## Summary
Metric | Value
Total Components | 7
Functions | 3
Procedures | 4
Ready for Migration | 5
Requires Refactoring | 2
Oracle-Specific Features | 5
Data Types to Map | 4
Estimated Total Effort | 10.5 hours
Overall Complexity | Medium
Migration Assessment | FEASIBLE - PROCEED

## Details
Component Name | Type | Status | Complexity | Effort (hrs) | Dependencies | Issues
new_customer | Function | Ready | Medium | 2 | Sequence setup | None
get_customer | Function | Ready | Low | 1 | None | None
get_customer_name | Function | Ready | Low | 0.5 | None | None
set_customer (v1) | Procedure | Ready | Low | 0.5 | None | None
set_customer (v2) | Procedure | Requires Refactoring | Medium | 2 | Overload resolution | Overloading not supported
delete_customer | Procedure | Ready | Low | 0.5 | None | None
purge_old_customers | Procedure | Requires Specification | Medium | 2.5 | Audit table definition | Audit trail logic not implemented

## Mappings
Oracle Feature | Snowflake Equivalent | Conversion Strategy | Risk Level
RETURNING Clause | Sequence or MAX() function | Use NEXTVAL() with explicit insert | Low
%type Declaration | Explicit type declaration | Define types explicitly | Low
%rowtype Declaration | OBJECT or VARIANT type | Use OBJECT_CONSTRUCT() | Medium
Procedure Overloading | Naming convention | Rename procedures with suffix | Medium
NO_DATA_FOUND Exception | NULL check or LIMIT 1 | Replace exception with NULL logic | Low
BOOLEAN Data Type | BOOLEAN type | Direct mapping | Low
NUMBER Type | BIGINT for IDs | Map to BIGINT | Low
VARCHAR2 Type | VARCHAR type | Direct mapping | Low
DATE Type | TIMESTAMP_NTZ | Direct mapping | Low

## Issues
Issue ID | Issue Title | Component | Severity | Description | Recommended Solution | Resolution Status
ISS-001 | Procedure Overloading Not Supported | set_customer | High | Snowflake does not support procedure overloading with same name but different signatures | Use naming convention: set_customer, set_customer_row | Pending
ISS-002 | Audit Trail Logic Not Implemented | purge_old_customers | Medium | TODO comment indicates audit trail deletion is not yet implemented | Define audit table schema and implement deletion logic | Pending
ISS-003 | RETURNING Clause Limited Support | new_customer | Medium | Snowflake has limited support for RETURNING clause | Implement sequence-based approach with NEXTVAL() | Pending
ISS-004 | %rowtype Not Directly Supported | get_customer, set_customer | Low | Snowflake does not have %rowtype anchor type | Define OBJECT type or use column-by-column approach | Pending
ISS-005 | No Data Found Exception Handling | get_customer, get_customer_name | Low | Oracle exception handling not available in Snowflake | Replace exception blocks with NULL value returns | Pending

## Metrics
Metric Category | Metric Name | Oracle Value | Snowflake Value | Change
Code Size | Total Functions | 3 | 3 | No change
Code Size | Total Procedures | 4 | 5 (one split due to overload) | +1 additional
Complexity | Components Ready | 7 | 5 | -2 requiring work
Effort | Estimated Hours | 0 | 10.5 | +10.5 hours
Data Types | Unique Types | 4 | 4 | Same count
Oracle Features | Features to Convert | 5 | 5 | All mapped

## Recommendations
Phase | Timeline | Action | Priority | Owner
Phase 1: Preparation | Week 1 | Define sequence strategy for auto-increment IDs | High | Database Architect
Phase 1: Preparation | Week 1 | Establish audit table schema and retention policies | High | Business Analyst
Phase 1: Preparation | Week 1 | Create Snowflake test environment | High | Infrastructure
Phase 2: Core Migration | Week 2 | Migrate get_customer and get_customer_name (simple reads) | High | Developer
Phase 2: Core Migration | Week 2 | Migrate delete_customer (simple deletes) | High | Developer
Phase 2: Core Migration | Week 2 | Migrate set_customer field-level variant | High | Developer
Phase 2: Core Migration | Week 2 | Migrate new_customer with sequence approach | High | Developer
Phase 3: Complex Components | Week 3 | Implement set_customer_row replacement procedure | Medium | Developer
Phase 3: Complex Components | Week 3 | Implement audit trail logic in purge_old_customers | High | Developer
Phase 4: Validation | Week 4 | Data migration validation and UAT | High | QA Team
Phase 4: Validation | Week 4 | Performance benchmarking and optimization | Medium | Database Performance